## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | team-swen-261-08-s2a-momo
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | Shubhang- 9/28/2020 | Pass | Shubhang- 9/28/2020
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | Joel 9/28/2020 | Pass | Joel 9/28/2020
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | Sasha 9/30/2020 | Pass | Sasha 9/30/2020
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | Quynh 10/1/2020 | Pass | Quynh 10/1/2020
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | Joel 10/1/2020 | Pass | Joel 10/1/2020
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | Shubhang & Quynh 10/1/2020 | Pass | Shubhang & Quynh 10/1/2020
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | Joel 10/1/2020 | Pass | Joel 10/1/2020
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Fail | Not developed or tested in Sprint 1 | Pass | JC - 10/6 |  | Sasha Persaud 10/25/2020 -The Player Lobby does not automatically refresh every 5 seconds to update the list of logged in players.
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Fail | Not developed or tested in Sprint 1 | Pass | JC - 10/6 |  | Sasha Persaud 10/25/2020
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Fail | Not developed or tested in Sprint 1 | Pass | JC - 10/6 |  | Sasha Persaud 10/25/2020 - Currently, players that are in a game are not shown in the Player Lobby.
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Fail | Not developed or tested in Sprint 1 | Pass | JC - 10/6 |  | Sasha Persaud 10/25/2020
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Fail | Not developed or tested in Sprint 1 | Pass | JC - 10/6 |  | Sasha Persaud 10/25/2020
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Fail | Not developed or tested in Sprint 1 | Pass | JC - 10/6 |  | Sasha Persaud 10/25/2020
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Fail | Not developed or tested in Sprint 1 | Pass | JC - 10/6 |  | Sasha Persaud 10/25/2020
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Fail | Not developed or tested in Sprint 1 | Pass | JC - 10/6 |  | Sasha Persaud 10/25/2020
Quit Game | Given that I'm playing a game when I view the Game page then I quit the game by either closing the window or pressing the Resign button | Fail | Not developed or tested in Sprint 1 | Pass | SM - 10/17 | Fail | Sasha Persaud 10/25/2020 -We should add AC for the cases in which a user is forced to quit a game because their opponent already resigned. Exit button doesn't work in the above case.
Turns | Given that I'm connected to another player and playing a game when I have to make the first move or the other person has made a move then I can make move by interacting with the pieces on the board. | [5 empty] | Sasha Persaud 10/25/2020 -Sometimes, between turns, pieces that were interacted with will disappear in the next turn.
| Given that I am supposed to go first when the game starts then I can make move by interacting with my pieces on the board. | [5 empty] | Sasha Persaud 10/25/2020
| Given that my opponent is supposed to go first when the game starts then they can make move by interacting with their pieces on the board. | [5 empty] | Sasha Persaud 10/25/2020
| Given that there is no winner yet when I already my move then my opponent should be able to make a move by interacting with their pieces on the board. | [5 empty] | Sasha Persaud 10/25/2020
| Given that there is no winner yet when my opponent already made their move then I should be able to make a move by interacting with my pieces on the board. | [5 empty] | Sasha Persaud 10/25/2020
Sign Out | Given that I'm signed in when I see the new home page then I can click a sign out button. | Fail | Not developed or tested in Sprint 1 | Pass | SP - 10/18 |  | Sasha Persaud 10/25/2020
| Given that I'm on the sign out page when I click the sign out button then I will be signed out of the webapp and redirected to the sign in page. | Fail | Not developed or tested in Sprint 1 | Pass | SP - 10/18 |  | Sasha Persaud 10/25/2020
| Given that I'm on the sign out page when I click the cancel button then I will be redirected to the home page and remain signed in. | Fail | Not developed or tested in Sprint 1 | Fail | JC - 10/20, The button brings you back to home page, but no longer signed in | Pass | Sasha Persaud 10/25/2020 JC 10/25 clicking no to signing out, brings you back to the homepage not signed out
Illegal Moves | **Given** that its my turn **when** I try to make a move **then** I should know whether the move is a valid move or not. | Fail | Not developed or tested in Sprint 1 | Pass | DS - 10/20
**Given** that its my turn **when** I try to make a simple move that is diagonal **then** the move should be valid.
**Given** that its my turn **when** I try to make a simple move that is not diagonal **then** the move should be invalid.
**Given** that its my turn **when** I try to make a jump move that is diagonal and over an opponent's piece **then** the move should be valid.
**Given** that its my turn **when** I try to make a jump move that is not diagonal and over an opponent's piece **then** the move should be invalid.
**Given** that its my turn **when** I try to make a jump move that is diagonal and not over an opponent's piece **then** the move should be invalid.
Simple Move | **Given** that I'm playing a game **when** I select a piece and make a valid diagonal simple move **then** my piece moves to an adjacent diagonal space
**Given** that I have done a simple move **when** I am ready to end my turn **then** I should be able to end my turn
**Given** that I have done a simple move **when** end my turn **then** my move should persist throughout my opponents turn
Simple Jump Move | **Given** that I'm making a move **when** I make a jump move **then** my piece goes over the opponents piece diagonally.
**Given** that I make a successful jump move **when** I complete the move **then** the opponents piece is captured
Required Jumps | **Given** that I'm playing a game **when** it is my turn and I click on a piece **then** I want to see all valid spaces where I can move
**Given** that I'm playing a game **when** I select a piece **then** I can change the selected piece without losing the turn
**Given** it is my turn **when** I want to end my turn and start my opponent's turn **then** the game should require me to do a move first
Multiple Jump Moves | **Given** I am able to capture another piece **when** I have already made a jump move **then** I expect the game to force me to capture the other piece
**Given** I have already made more than one jump, **when** I cannot make any more jumps, **then** I expect the game to pass the turn to my opponent
**Given** I have already made more than one jump **when** I attempt to jump over one of my own pieces **then** I expect the game to reject my move.
King Piece | **Given** its my turn **when** my piece gets to the last row **then** I expect to become a King Piece
**Given** that a regular piece is crowned to be a King piece **when** it reaches the opponent's last row **then** I expect the King Piece to now be able to move forward.
**Given** that a regular piece is crowned to be a King piece **when** it reaches the opponent's last row **then** I expect the King Piece to now be able to move backward.
**Given** that a regular piece is crowned to be a King piece **when** it reaches the opponent's last row **then** I expect the King Piece to retain the mobility of a regular piece, i.e. move diagonally and make jumps.
Show Captured Pieces | **Given** that I am signed into a game **when** neither I nor my opponent has made a move yet, **then** I shouldn't see any captured pieces along the side of the board.
**Given** that I am in a game **when** I capture one of my opponent's regular pieces **then** the piece I captured will be displayed along my right side of the board.
**Given** that I am in a game **when** my opponent captures one of my regular pieces, **then** the piece he/she captured will be displayed along my left side of the board.
**Given** that I am in a game **when** either me or my opponent captures the other's king piece **then** the king piece will be displayed along the respective side of the board (right for me, left for my opponent) and will look distinctively different than the regular pieces.
Display Kings | **Given** I am in a game **when** a piece has reached the opposite side of the board **then** the piece should become a king
**Given** that a piece is turned into King piece **when** it reaches the opponent's end of the board **then** the piece should have a crown on it to show that it is no longer a regular piece.
**Given** that a King piece is captured **when** an opponent's piece has jumped over it **then** the piece should be displayed with a crown on the side of the checker board.
Show Winner | **Given** I win the game **when** my opponent forefits **then** I expect to see my name on a win screen
**Given** I win the game **when** I captures all of my opponent's pieces **then** I expect to see my name on a win screen
**Given** I lose the game **when** I forefit **then** I expect to see my opponent's name on a win screen
**Given** I lose the game **when** my opponent captures all of my pieces **then** I expect to see my opponent's name on a win screen
**Given** the game has ended **when** someone has won the game **then** I expect to have the ability to go back to the homepage